## Up to 100 kWp (4mo)
| Start Date = | 2026-08-12 | <----- Change this date
Sr. | Item Description | 2026-09-12 | 2026-10-12 | 2026-11-12 | 2026-12-12
1 | PPA Signing
2 | Customer Kick-Off Meeting
3 | Site Handover / Design Approval (whichever later)
4 | Mobilization of team at site
5 | Procurement
6 | Civil Work, Installation & Cabling
7 | Pre Commissioning & Test Charge
8 | Liasoning
9 | Site Acceptance Test
10 | Handover
11 | Project Closure
| Start Date = | 2026-08-12 |  | Project End Date = | 2026-12-12

## 100-1000 kWp (5mo)
| Today = | 2026-08-12 | <----- Change this date
Sr. | Item Description | 2026-09-12 | 2026-10-12 | 2026-11-12 | 2026-12-12 | 2027-01-12
1 | PPA Signing
2 | Customer Kick-Off Meeting
3 | Site Handover / Design Approval (whichever later)
4 | Procurement
5 | Mobilization of team at site
6 | Civil Work, Installation & Cabling
7 | Pre Commissioning & Test Charge
8 | Liasoning
9 | Site Acceptance Test
10 | Handover
11 | Project Closure
| Start Date = | 2026-09-12 |  |  | Project End Date = | 2027-01-12

## Above 1000 kWp (6mo)
| Today = | 2026-08-12 | <----- Change this date
Sr. | Item Description | 2026-09-12 | 2026-10-12 | 2026-11-12 | 2026-12-12 | 2027-01-12 | 2027-02-12
1 | PPA Signing
2 | Customer Kick-Off Meeting
3 | Site Handover / Design Approval (whichever later)
4 | Mobilization of team at site
5 | Procurement
6 | Civil Work, Installation & Cabling
7 | Pre Commissioning & Test Charge
8 | Liasoning
9 | Site Acceptance Test
10 | Handover
11 | Project Closure
| Start Date = | 2026-09-12 |  |  | Project End Date = | 2027-02-12

## Above 1000 kWp (12mo)
| Today = | 2026-08-12 | <----- Change this date
Sr. | Item Description | 2026-09-12 | 2026-10-12 | 2026-11-12 | 2026-12-12 | 2027-01-12 | 2027-02-12 | 2027-03-12 | 2027-04-12 | 2027-05-12 | 2027-06-12 | 2027-07-12 | 2027-08-12
1 | PPA Signing | bar: 2026-09-12
2 | Customer Kick-Off Meeting | bar: 2026-09-12 to 2026-10-12
3 | Site Handover / Design Approval (whichever later) | bar: 2026-09-12 to 2026-10-12
4 | Mobilization of team at site | bar: 2026-09-12 to 2026-10-12
5 | Procurement | bar: 2026-09-12 to 2027-01-12
6 | Civil Work, Installation & Cabling | bar: 2026-10-12 to 2027-01-12
7 | Pre Commissioning & Test Charge | bar: 2026-10-12 to 2027-01-12
8 | Liasoning | bar: 2026-11-12 to 2027-06-12
9 | Site Acceptance Test | bar: 2027-01-12 to 2027-08-12
10 | Handover | bar: 2027-07-12 to 2027-08-12
11 | Project Closure | bar: 2027-08-12
| Start Date = | 2026-09-12: 2026-09-12; 2027-05-12: Project End Date =; 2027-06-12: 2027-10-12